## Sheet1
Task | Project Leader | Start Date | End Date | 02 Mar-08 Mar | 09 Mar-13 Mar | 16 Mar-20 Mar | 23 Mar-27 Mar | 30 Mar-03 Apr | 06 Apr-11 Apr | 13 Apr-17 Apr | 20 Apr-24 Apr | 27 Apr-01 May | 04 May-08 May | 11 May-15 May | 18 May-22 May | 25 May-29 May | 01 Jun-05 Jun
Planning and research | Nosipho & Anele & Phumelele | 08/02/2026 | 18/03/2026
Market Research Report | Nosipho & Anele & Phumelele | 08/02/2026 | 13/03/2026
Project Plan | Nosipho & Anele & Phumelele | 16/03/2026 | 18/03/2026
Design and Prototyping | Anele & Phumelele | 16/03/2026 | 23/03/2026
User Interface Design | Phumelele | 16/03/2026 | 18/03/2026
Prototype Development | Anele | 18/03/2026 | 23/03/2026
Development | Noluthando & Anele | 30/03/2026 | 24/04/2026
Backend Development | Noluthando | 11/04/2026 | 20/04/2026
Frontend Development | Anele | 30/03/2026 | 10/04/2026
Testing and Quality Assurance | Nosipho & Phumelele | 20/04/2026 | 28/04/2026
Testing and Bug Fixing | Nosipho | 20/04/2026 | 24/04/2026
Performance Optimization | Phumelele | 24/04/2026 | 28/04/2026
Launch and Marketing | Nosipho & Noluthando | 11/05/2026 | 01/06/2026
Launch Preparation | Noluthando | 11/05/2026 | 20/05/2026
Marketing and Promotion | Nosipho | 25/05/2026 | 01/06/2026